Project Management Plan

Tutor Connect System (TCS) - Report 2

| Project Name | Tutor Connect System (TCS) |
| --- | --- |
| Vision & Scope Ref | Vision & Scope Document v1.1 |
| RTW Ref | TCS_Report 3.1 RTW.xlsx (Requirements Traceability Workbook) |
| Plan Version | v1.1 |
| Date Created | 15/05/2026 |
| Last Updated | 13/05/2026 |
| Author(s) | Nguyen Trung Kien |
| Reviewer(s) | Hoang Khoi Nguyen |
| Status | In Review |

# 1. Overview

## 1.1 Cost/Time Estimation

| # | Work Package | Est. Effort (pds) | Deadline |
| --- | --- | --- | --- |
| Stage 1: Project Initiating (Week 1) |  |  |  |
| 1.1 | Report 1 (Project Introduction) | 5 | Week 1 |
| Stage 2: Project Planning & Initial Requirements (Weeks 2–3) |  |  |  |
| 2.1 | Report 2: Project Management Plan v1.0 | 5 | Week 2 |
| 2.2 | Report 3: SRS v0.9 (Overall Requirement) | 3 | Week 2 |
| 2.3 | Vertical Prototypes (Code Demo) | 3 | Week 3 |
| Stage 3: Software Design (Weeks 4–5) |  |  |  |
| 3.1 | Vertical Prototypes (POC — Proof of Concepts) | 4 | Week 4 |
| 3.2 | Report 4: SDS v1.0 (High-Level Design Specifications) | 5 | Week 4 |
| 3.3 | Report 5: Test Planning | 5 | Week 5 |
| 3.4 | Report 3: SRS v1.0 (Detailed Requirements for Iteration 1) | 3 | Week 5 |
| Stage 4: Implementation (Weeks 6–11) |  |  |  |
| 4.1 Implementation Iteration 1 (Weeks 6–7) |  |  |  |
| 4.1.1 | Report 4: SDS v1.1 (Detailed Design Specifications) | 3 | Week 6 |
| 4.1.2 | Code Package & Unit Testing Report | 4 | Week 6 |
| 4.1.3 | Report 5: Integration Test Cases | 3 | Week 6 |
| 4.1.4 | Report 5: Integration Test Report | 3 | Week 7 |
| 4.1.5 | Report 3: SRS v1.1 (Detailed Requirements for Iteration 2) | 3 | Week 7 |
| 4.1.6 | Software Package Version 1 | 5 | Week 7 |
| 4.2 Implementation Iteration 2 (Weeks 8–9) |  |  |  |
| 4.2.1 | Report 4: SDS v1.2 (Detailed Design Specifications) | 3 | Week 8 |
| 4.2.2 | Code Package & Unit Testing Report | 4 | Week 8 |
| 4.2.3 | Report 5: Integration Test Cases | 3 | Week 8 |
| 4.2.4 | Report 5: Integration Test Report | 3 | Week 9 |
| 4.2.5 | Report 3: SRS v1.2 (Detailed Requirements for Iteration 3) | 3 | Week 9 |
| 4.2.6 | Software Package Version 2 | 5 | Week 9 |
| 4.3 Implementation Iteration 3 (Weeks 10–11) |  |  |  |
| 4.3.1 | Report 4: SDS v1.3 (Detailed Design Specifications) | 3 | Week 10 |
| 4.3.2 | Code Package & Unit Testing Report | 4 | Week 10 |
| 4.3.3 | Report 5: Integration Test Cases | 3 | Week 10 |
| 4.3.4 | Report 5: Integration Test Report | 3 | Week 11 |
| 4.3.5 | Report 5: System Test Cases | 3 | Week 11 |
| 4.3.6 | Software Package Version 3 | 5 | Week 11 |
| Stage 5: Verification & Validation (Weeks 12–13) |  |  |  |
| 5.1 | Report 5: System Test Report | 2 | Week 12 |
| 5.2 | Report 6: User Guides (Installation Guide, User Manual) | 4 | Week 12 |
| 5.3 | Acceptance Test and Support | 3 | Week 13 |
| 5.4 | Final Software Package (Documents, Source Codes, etc.) | 5 | Week 13 |
| Stage 6: Closing (Week 14) |  |  |  |
| 6.1 | Report 7: Final Project Report | 5 | Week 14 |
| 6.2 | Presentation File | 5 | Week 14 |

## 1.2 Project Objectives

| # | Metric | Unit | Planned | Actual | Notes / References |
| --- | --- | --- | --- | --- | --- |
| 1 | Effort Usage | Person-day | 116 |  |  |
| 2 | Number of Defect | No. of defects |  |  |  |
| 3 | Timeliness | % | 100 |  |  |
| 4 | Requirement Completeness | % | 100 |  |  |
| 5 | Plagiarism Rate | % | < 15 |  |  |
| 6 | Test Case Pass Rate | % | ≥ 95 |  |  |

## 1.3 Project Risks

| # | Risk Description | Impact | Possibility | Priority | Response Plans (Mitigation / Contingency) |
| --- | --- | --- | --- | --- | --- |
| 1 | Reliance on third-party services and APIs may affect development and integration schedules. | Medium | Medium | 4 | Test with WireMock stubs; fall back to manual entry if integration fails. |
| 2 | Changes in requirements after approval may lead to scope creep and project delays. | Medium | High | 6 | Enforce strict ChangeLog controls; defer low-priority features with PO if needed. |
| 3 | AI-based matching and real-time communication features may require more effort than initially estimated. | Medium | High | 6 | Apply strict prompt engineering and validation; fall back to static rule-based results. |
| 4 | Unavailability of key team members may impact project continuity and delivery schedule. | Medium | Medium | 4 | Cross-train members via shared knowledge base; reassign tasks or escalate to instructor. |
| 5 | Ineffective communication and task coordination may delay project milestones. | Low | High | 3 | Track tasks via centralized Kanban; PM reallocates delayed tasks immediately. |

# 2. Management Approach

## 2.1 Project Processes

### a) Development Methodology

The project adopts a Hybrid methodology, blending the structured framework of the Waterfall model with the flexibility of the Iterative and Incremental (I&I) approach. This combination is optimized for the 4 month timeline of a graduation thesis, ensuring both academic rigor and software flexibility.

- Waterfall phases (Initial & Final stages): The first 3-4 weeks are dedicated to requirement gathering, system architecture, and database design. Similarly, the final weeks focus on comprehensive testing and final thesis documentation.

- Iteration & Incremental phases (Development stage): The core coding phases (Front-end and Back-end) is divided into 2-3 weeks iterations. Each iteration repeats the cycle of Coding → Internal Testing → Bug Fixing → Demo. This ensures that a working prototype is always available for progress reviews with the thesis advisor, minimizing the risk of integration failure at the deadline.

### b) Project Management Sub-processes

- Scope Management: The project concept is deconstructed into a clear Product Backlog during the first month to prevent scope creep. Requirements are prioritized using  the MoSCoW technique (Must-Have, Should-Have, Could-Have) and Must-Have features must be completed and stable before moving on to higher-tier features.

- Change Management: Any requested modification is formally logged and undergoes an impact analysis to evaluate its effect on the database schema, development effort, and deadlines. If a proposed change severely threatens the project schedule, it is rejected for the current release and deferred to the "Future Work" section of the thesis.

- Time Management: Gantt Chart that outlines the master schedule, weekly tasks, and critical academic milestones. Daily and weekly progress is monitored using a digital Kanban Board on Jira to track the workflow of tasks from To Do to Done, while all source code and development versions are centrally managed on GitHub.

- Issue Management: All unexpected problems are logged on GitHub Issues, Google sheet and categorized by severity, ensuring that high-priority system blockers are resolved immediately. Once a developer fixes an issue, another team member must independently verify the solution before it is formally closed.

## 2.2 Quality Management

### a) Defect Prevention

Defect prevention focuses on minimizing coding errors early by establishing clear requirements and robust system architecture before the development phase begins. The team conducts thorough database schema reviews and aligns technical specifications with the thesis advisor to eliminate ambiguities. Additionally, potential risks such as security vulnerabilities or data loss are identified early to implement preventative validation logic in both the frontend and backend.

### b) Peer Reviews

Peer reviews are integrated directly into the development workflow using GitHub pull requests to ensure code quality and knowledge sharing within the team. Before any new feature branch is merged into the main repository, another team member must review the source code for logic errors, security flaws, and architectural consistency. Feedback and requested changes are tracked directly on GitHub, guaranteeing that only verified and high-quality code enters the production build.

### c) Unit Testing

Unit testing is utilized during each development iteration to verify that individual components, functions, and API endpoints perform exactly as isolated requirements dictate. Developers write automated test scripts alongside their core logic to quickly identify regressions or broken functionality whenever code changes occur. Test execution results and code coverage metrics are monitored regularly to ensure the website’s backend logic remains stable and reliable.

### d) Code Standards

To maintain a clean, readable, and easily maintainable codebase, the team strictly adheres to industry-standard coding conventions and formatting guidelines for both frontend and backend languages. Automated linting tools are integrated into the development environment to automatically enforce consistent naming conventions, file structures, and syntax rules across all team members. These unified standards prevent technical debt and ensure that the project can be smoothly evaluated or expanded during the thesis defense.

## 2.3 Project Training Plan

| Training Area | Participants | When / Duration |
| --- | --- | --- |
| Java Spring Boot | All members | Week 1-2 (2 weeks) |
| ReactJS (Front-end) | All members | Week 1-2 (2 weeks) |
| MySQL Database Design | All members | Week 1 (3 days) |
| Git & GitHub | All members | Week 1 (2 days) |
| RESTful API Development | All members | Week 2 (3 days) |
| WebSocket & Real-time Communication | Real-time features team | Week 5 (2 days) |
| PayOS/VietQR Integration | Payment system team | Week 6 (2 days) |
| AI API Integration | AI & Analytics team | Week 7 (2 days) |
| Testing & Debugging Techniques | Testing team | Week 9 (2 days) |
| Deployment & CI/CD | PM & Deploy members | Week 10 (2 days) |

# 3. Responsibility Assignments

| Work Package | KienNT | AnhNT | NguyenHK | KhanhVQ | DucHM |
| --- | --- | --- | --- | --- | --- |
| R = Responsible ¦ A = Accountable ¦ C = Consulted ¦ I = Informed |  |  |  |  |  |
| Report 1 – Project Introduction | A | R | R | R | R |
| Report 2 – Project Management Plan v1.0 | R | C | A | C | C |
| Report 3 – SRS v0.9 (Overall Requirement) | A | R | I | I | I |
| Vertical Prototypes (Code Demo) | A | - | - | - | R |
| Vertical Prototypes (POC - Proof of Concepts) | A | - | - | - | R |
| Report 4 – SDS v1.0 (High-Level Design Specifications) | A | I | I | I | R |
| Report 5 – Test Planning | A | I | R | I | I |
| Report 3 – SRS v1.0 (Detailed Requirement for Iteration 1) | A | R | I | I | I |
| Report 4 – SDS v1.1 (Detailed Design Specifications) | A | I | I | I | R |
| Code Package & Unit Testing Report | C | A | R | R | - |
| Report 5 – Integration Test Cases (Iteration 1) | A | I | R | C | I |
| Report 5 – Integration Test Report (Iteration 1) | A | I | R | C | I |
| Report 3 – SRS v1.1 (Detailed requirements for Iteration 2) | A | R | I | I | I |
| Software Package Version 1 | R | - | - | - | A |
| Report 4 – SDS v1.2 (Detailed Design Specifications) | A | I | I | I | R |
| Code Package & Unit Testing Report | C | - | R | R | A |
| Report 5 – Integration Test Cases (Iteration 2) | A | I | R | C | I |
| Report 5 – Integration Test Report (Iteration 2) | A | I | R | C | I |
| Report 3 – SRS v1.2 (Detailed Requirements for Iteration 3) | A | R | I | I | I |
| Software Package Version 2 | R | - | - | A | - |
| Report 4 – SDS v1.3 (Detailed Design Specifications) | A | I | I | I | R |
| Code Package & Unit Testing Report | C | A | R | R | - |
| Report 5 – Integration Test Cases (Iteration 3) | A | I | C | R | I |
| Report 5 – Integration Test Report (Iteration 3) | A | I | C | R | I |
| Report 5 – System Test Cases | A | I | I | R | I |
| Software Package Version 3 | R | A | - | - | - |
| Report 5 – System Test Report | A | I | I | R | I |
| Report 6 – User Guides (Installation Guide, User Manual) | A | I | I | R | I |
| Acceptance Test and Support | C | - | - | A | R |
| Final Software Package (Documents, Source Codes, etc.) | R | I | A | I | I |
| Report 7 – Final Project Report | R | C | C | C | A |
| Presentation File | A | R | I | I | I |

# 4. Project Communications

| Communication Item | Who / Target | Owner | Purpose | When / Frequency | Type / Tool |
| --- | --- | --- | --- | --- | --- |
| Daily Meeting | All members | PM | Quick discussion and daily report. | Daily | Offline/Online, Google meet, Group chat |
| Weekly Meeting | All members | PM | Review progress, discuss blockers, assign next tasks. | Weekly (SUN) | Offline/Online, Google Meet, Group chat |
| Supervisor Meeting | All members, Lecturer | Lecturer | Report project progress and receive feedback. | Weekly (WED/SAT) | Offline/Online, Google meet |
| Mentor Meeting | All members, Mentor | Mentor | Technical consultation and architecture guidance. | Weekly (TUE&FRI) | Offline/Online, Google meet |
| Task Assignment And Tracking | All members | PM | Monitor tasks and progress. | Continuous | Jira, Google sheet |
| Source Code Management | All members | Tech Lead | Manage source code and version control. | Continuous | Github, Pull request workflow |
| UI/UX Discussion | All members | PM | Review interface design and user experience. | During UI/UX phases | Figma |
| Testing & Bug Reporting | Tester team | Test Leader | Report and track defects/issues. | During testing phases | GitHub Issues, Google sheet |
| Documentation Review | All members | PM | Ensure consistency and quality of report/documents | Before submission deadlines | Google docs/sheet, Microsoft word |
| Final Defense Preparation Meeting | All members | PM | Prepare presentation slides, demo flow, and Q&A practice. | Final 2 weeks | Offline/Online, Google meet |

# 5. Configuration Management

## 5.1 Document Management

### a) Document Storage and Organization

All major project artifacts—including Reports 1–7, the Software Requirements Specification (SRS), Software Design Description (SDD), test documents, user guides, and meeting minutes—are centrally stored and managed within categorized folders on Google Drive. This cloud-based infrastructure ensures seamless collaboration, prevents data fragmentation, and provides an organized repository for all academic and technical files. The Project Manager is responsible for organizing these folders, reviewing contents, and ensuring that all artifacts are correctly aligned with the university's graduation milestones.

### b) Naming Convention and Version Control

To maintain structural clarity and track document updates, the team enforces a strict, standardized naming convention that embeds the document title, version number, and last modification date (e.g., [Document_Name] v[X.X]). Minor edits during internal collaboration increment the decimal version (e.g., v1.1), while major milestones or final advisor-approved versions advance the principal number (e.g., v2.0). Google Docs' built-in revision history is heavily utilized to log exact changes, maintain backup copies of critical drafts, and allow the team to roll back to previous iterations if necessary.

### c) Access Control and Change Review

Access control is managed through Google Drive's permission settings, granting full editing rights exclusively to internal team members while providing read-only access to external stakeholders, such as the thesis advisor, when feedback is required. Before any critical document is finalized for a milestone submission, a mandatory peer review process is initiated within the team to ensure quality, accurate formatting, and total consistency across all chapters. This collaborative validation ensures that no unauthorized or unverified changes slip into the final reports presented to the graduation committee.

## 5.2 Source Code Management

### a) Branching Strategy

| Branch | Purpose | Naming Convention | Protection |
| --- | --- | --- | --- |
| main | Production code | main | Required reviews, CI passing |
| develop | Integration branch | develop | Required reviews |
| feature/ | New features | feature/UC-XX-login | CI optional |
| bugfix/ | Bug fixes | bugfix/issue-XX-otp | CI optional |
| hotfix/ | Production fixes | hotfix/description | Fast-track review |
| release/ | Release preparation | release/v1.0.0 | Release manager |

### b) Commit Conventions

| Type | Description | Example |
| --- | --- | --- |
| feat | New feature | feat(auth): add user login |
| fix | Bug fix | fix(class):resolve class conflict |
| docs | Documentation | docs(api):update API documentation |
| style | Formatting | style(class):format code with prettier |
| refactor | Code improvement | refactor(auth):extract auth service |
| test | Adding tests | test(class):add unit tests for class |
| chore | Maintenance | chore:update dependencies |
| pref | Performance | pref(class):optimize query for search |
| ci | CI/CD changes | ci:add GitHub Actions workflow |

### c) Code Review and Integration Process

| Steps | Description |
| --- | --- |
| Create branch | $ git checkout -b feature/UC-01-login |
| Make changes & commit | $ git add . $ git commit -m "feat(auth): add login form" |
| Push to remote | $ git push origin feature/UC-01-login |
| Create pull request | 1. GitHub PR Template 2. Select reviewers 3. Link to issue |
| CI/CD pipeline | 1. Lint check 2. Unit tests 3. Build check 4. Security scan |
| Code review | 1. At least 2 approvals required 2. All comments resolved 3. All checks passing |
| Merge | 1. Squash and marge 2. Delete branch 3. Auto-deploy to staging |

## 5.3 Tools & Infrastructure

| Category | Tools / Infrastructure |
| --- | --- |
| Technology | ReactJS (Front-End), Spring Boot (Back-End), RESTful API, WebSocket |
| Database | MySQL 8.0 CE, Firebase |
| IDEs / Editors | IntelliJ IDEA |
| Diagramming | Visual Paradigm, PlantUML, draw.io V28.1.2 |
| Documentation | MS Office 2019, Google Docs / Sheets / Slides |
| Version Control | GitHub (Source Codes), Google Drive (Documents) |
| Deployment Server | Amazon Web Services (AWS) |
| Project Management | Jira (tasks), Google sheet (tasks, time logs, defects, issues) |

— End of Document —