Project Management Plan

Tutor Connect System (TCS) – Report 2

| Version | v1.3 |
| --- | --- |
| Date | 03/07/2026 |

# Change Log

| Version | Date | Author | Summary |
| --- | --- | --- | --- |
| v1.0 | 15/05/2026 | Nguyen Trung Kien | Initial plan |
| v1.1 | 13/06/2026 | Nguyen Trung Kien | Update project risks |
| v1.2 | 18/06/2026 | Nguyen Trung Kien | Update project scope |
| v1.3 | 03/07/2026 | Nguyen Trung Kien | Change the workflow on a case-by-case basis. |

# Table of Contents

Change	1

Table of Contents	2

1. Project Overview	3

1.1 System Description	3

1.2 Technical Scope Summary	3

2. Development Team	3

2.1 Team Structure	3

2.2 RACI by Deliverable Type	4

2.3 Capacity Planning	4

3. Deliverable & Scope	5

3.1 Timeline Overview	5

3.2 Project Deliverables	5

3.3 Scope and Workload	6

4. Risks and Mitigations	9

5. Communication Plan	9

6. Configuration Management	10

6.1 Document Management	10

6.2 Source Code Management	10

6.3 Tools & Infrastructures	12

# 1. Project Overview

## 1.1 System Description

Tutor Connect System (TCS) is a web-based platform that connects clients, tutors, and tutor centers by providing tutor matching, class management, and escrow payment services. It centralizes tutor discovery, communication, and transaction management into a single integrated system.

## 1.2 Technical Scope Summary

| Metric | Value |
| --- | --- |
| Business Flows | 11 Business Flows (BF-01 User Registration & Service Provider Verification, BF-02 Tutor Recruitment for On-Demand Class, BF-03 Tutor Recruitment for Center Workforce, BF-04 Curriculum-Based Class Creation & Enrollment, BF-05 On-Demand Class Management, BF-06 Curriculum-Based Class Management, BF-07 Wallet & Payment Management, BF-08 Review & Reputation Management, BF-09 Issue, Dispute & Refund Management, BF-10 Customer Support, BF-11 Platform Administration & Analytics) |
| Actors / Roles | 4 Roles (Platform Admin, Client, Tutor Center, Tutor) |
| Use Cases | 71 Use Cases (UC-01 → UC-7) |
| Total FT-IDs | 51 (Must: 41, Should: 9, Could: 1) |
| Screens / Pages | 67 (SCR-01 → SCR-67) |
| Background Jobs | 13 (JOB-01 Verification Approval Job, JOB-02 Tutor Recommendation Job, JOB-03 Dynamic Matching Job, JOB-04 Schedule Conflict Detection Job, JOB-05 Notification Dispatcher Job, JOB-06 Contract Generation Job, JOB-07 Escrow Release Job, JOB-08 Refund Processing Job, JOB-09 Reputation Score Calculation Job, JOB-10 Stale Escrow Sweeper Job, JOB-11 Platform Circumvention Scanner Job, JOB-12 Analytics Aggregation Job, JOB-13 Audit Log Archival Job) |

# 2. Development Team

## 2.1 Team Structure

| Role | Code | Primary responsibilities |
| --- | --- | --- |
| Tech Lead | TL | System Architecture, Code Review, Technical Design Specification (TDS), Deployment Guide. Pair programming and unblocking Devs across both FE and BE. |
| Business Analyst / PM | BA | PRD, UCS (all iterations), FDS (all iterations), User Manual, Handover Report, Sprint Facilitation (Scrum Master role). |
| Developer 1 | D1 | End-to-End feature development (FE + BE + L1/L2 Tests) assigned per Sprint. Secondary focus: UI-UX & Front-end Architecture champion. |
| Developer 2 | D2 | End-to-End feature development (FE + BE + L1/L2 Tests) assigned per Sprint. Secondary focus: Database Optimization & DevOps support for TL. |
| QA Lead (Tester) | QA | Test Plan, L3 System, L3-SCH Scheduler, L4 E2E, UAT Coordination. Implements the Admin module and background jobs, or the Automation Test Framework, in Iteration 3. |

## 2.2 RACI by Deliverable Type

R~Responsible (does the work)  ·  A~Accountable (approves quality)  ·  C~Consulted  ·  I~Informed

| Deliverable | TL | BA | D1 | D2 | QA |
| --- | --- | --- | --- | --- | --- |
| Vision & Scope | C | R | I | I | I |
| PRD | C | R | C | C | C |
| TDS | R | C | C | I | C |
| UCS | C | R | C | C | C |
| FDS | C | R | I | I | C |
| Test Plan | C | C | C | C | R |
| Feature code — [Module 1+2+3] | A | I | R | I | I |
| Feature code — [Module 4+5+6] | A | I | I | R | I |
| Feature code — [Module 7+8+9] | A | I | R | R | I |
| Feature code — [Admin / BG jobs] | A | I | C | C | R |
| L1 Unit tests | A | I | R | R | C |
| L2 Integration tests | C | I | R | R | C |
| L3 System tests | C | I | I | I | R |
| L4 UAT scripts execution | I | C | I | I | R |
| Deployment Guide | R | C | I | I | I |
| User Manual | C | R | I | I | C |
| Final Report | C | R | I | I | C |

## 2.3 Capacity Planning

| Item | Value |
| --- | --- |
| Hours per person per week | 30h (6h/day × 5 days) |
| Team total per week | 150h/week (5 person × 30h) |
| Total duration | 14 weeks |
| Gross capacity | 2100h (150h/week × 14 weeks) |
| Buffer (meetings, reviews, unplanned — 20%) | 420h |
| Effective working capacity | 1680h |

# 3. Deliverable & Scope

## 3.1 Timeline Overview

Week  │ 1  │ 2  │ 3  │ 4  │ 5  │ 6  │ 7  │ 8  │ 9  │10  │11  │12  │13  │14  │

──────┼────┼────┼────┼────┼────┼────┼────┼────┼────┼────┼────┼────┼────┼────┤

Phase │◄─────── Phase 1 ──────►│◄──────────── Phase 2 ───────────►│◄P3►│IV  │

│Plan & High-Level Design│ Iter 1  │ Iter 2  │ Iter 3  │    │    │    │

──────┼────┼────┼────┼────┼────┼────┼────┼────┼────┼────┼────┼────┼────┼────┤

TL    │    │Arch│TDS │TDS │Rev │Code│Code│Code│Code│Code│DG  │E2E │E2E │E2E │

BA    │V&S │PRD │PP  │UCS1│FDS1│UCS2│FDS2│UCS3│FDS3│E2E │E2E │UM  │UM  │FR  │

D1    │ -  │ -  │Env │Code│Rev │Code│Test│Code│Test│Code│Test│E2E │E2E │UAT │

D2    │ -  │ -  │Env │Code│Rev │Code│Test│Code│Test│Code│Test│E2E │E2E │UAT │

QA    │ -  │ -  │ -  │TP  │Rev │Rev │L3  │Rev │L3  │Rev │L3  │L4  │L4  │AT  │

──────┴────┴────┴────┴────┴────┴────┴────┴────┴────┴────┴────┴────┴────┴────┘

Key: V&S=Vision&Scope · Arch=Architecture · PRD=Product Req · UCS=Use Case Spec

FDS=Feature Design Spec · TP=Test Plan · PP=Project Plan · Rev=Review

Env=Environment setup · UM=User Manual · DG=Deployment Guide

FR=Final Report

## 3.2 Project Deliverables

| Deliverable | Completion phase / Deadline | Owner |
| --- | --- | --- |
| Vision & Scope | Phase 1 — Week 1 | BA |
| PRD v1.0 | Phase 1 — Week 2 | BA |
| TDS v1.0 | Phase 2 — Week 3 | Tech Lead |
| UCS v1.0 (preliminary) | Phase 1 — Week 4 | BA |
| FDS v1.0 (preliminary) | Phase I — Week 4 | BA |
| Test Plan §I–IV | Phase I — Week 5 | QA Lead |
| Project Plan v1.0 | Phase I — Week 5 | BA |
| UCS detailed (per iteration) | Phase 2 — Weeks 6, 8, 10 | BA + Dev |
| FDS detailed (per iteration) | Phase 2 — Weeks 7, 9, 11 | BA |
| Software package (per iteration) | Phase 2 — Weeks 7, 9, 11 | TL + Dev |
| UT/IT/ST Test Report (per iteration) | Phase 2 — Weeks 7, 9, 11 | QA Lead |
| Test Plan §V (Report) | Phase 3 | QA Lead |
| Deployment Guide | Phase 3 | Tech Lead |
| User Manual | Phase 3 | BA |
| Final Report | Phase 3 | BA |

## 3.3 Scope and Workload

1) Iteration 1 (Weeks 6 – 7)

Foundation: User Onboarding, Tutor Discovery, Class Management, and Secure Transaction

| FT-ID | Feature name | Priority | Module | UC-ID | SCR-ID |
| --- | --- | --- | --- | --- | --- |
| FT-01 | User Registration | Must | Auth & RBAC | UC-02 | SCR-02 |
| FT-02 | User Login | Must | Auth & RBAC | UC-01 | SCR-03 |
| FT-04 | Role-Based Access Control | Must | Auth & RBAC | — | SCR-07 |
| FT-05 | Manage User Profile | Must | Profile & Verification | UC-08 | SCR-06 |
| FT-06 | Tutor Credential Upload | Must | Profile & Verification | UC-09 | SCR-08 |
| FT-07 | Center License Submission | Must | Profile & Verification | UC-10 | SCR-08 |
| FT-08 | Verification Approval Workflow | Must | Profile & Verification | UC-11 | SCR-09, SCR-55 |
| FT-09 | Search Tutors & Classes | Must | Advanced Search | UC-31, UC-32 | SCR-10, SCR-16 |
| FT-10 | View Tutor / Class Detail | Must | Advanced Search | UC-33, UC-34 | SCR-11, SCR-17 |
| FT-12 | Class Creation & Pipeline | Must | Class Life-cycle | UC-14, UC-23 | SCR-15, SCR-21 |
| FT-13 | Student Data Import/Export | Must | Class Life-cycle | UC-19, UC-20 | SCR-30, SCR-31 |
| FT-14 | Apply To Class | Must | Class Life-cycle | UC-16, UC-17 | SCR-17, SCR-18 |
| FT-15 | Manage Class Status | Must | Class Life-cycle | UC-14, UC-21 | SCR-20, SCR-22 |
| FT-31 | Tutor Assignment Engine | Must | Class Life-cycle | UC-15 | SCR-19 |
| FT-48 | Select Tutor for Class | Must | Class Life-cycle | UC-22 | SCR-18 |
| FT-18 | Internal Chat | Must | Messaging & Notification | UC-36 | SCR-35 |
| FT-21 | Lesson Scheduling | Must | Class Life-cycle | UC-18, UC-25 | SCR-28 |
| FT-50 | Payment Method & Wallet Management | Must | Smart Escrow Wallet | UC-38, UC-39 | SCR-39, SCR-41 |
| FT-24 | Auto Contract Generation | Must | Smart Escrow Wallet | UC-44, UC-45 | SCR-34, SCR-42 |
| FT-25 | Escrow Deposit | Must | Smart Escrow Wallet | UC-40 | SCR-40 |
| FT-26 | Escrow Release | Must | Smart Escrow Wallet | UC-40 | SCR-42, SCR-45 |
| FT-36 | User Management | Must | Operations Dashboard | UC-07 | SCR-54 |
| FT-37 | Verification Management | Must | Profile & Verification | UC-11 | SCR-55 |
| FT-39 | Escrow & Financial Monitoring | Must | Operations Dashboard | UC-41, UC-43, UC-58 | SCR-58, SCR-60 |
| FT-47 | System Category & Fee Configuration | Must | Operations Dashboard | UC-46, UC-57 | SCR-62, SCR-64 |

ℹ End-of-Iteration-1 outcome: [Describe what a user can actually do after this iteration — e.g. 'HR Manager can sign in and manage job postings through their full lifecycle.']

Users can register, authenticate and access role-scoped areas; tutors/centers submit credentials & licenses for admin verification. Clients can search tutors and classes, create tutoring requests, assign/select tutors, apply to classes, chat internally, schedule lessons, sign auto-generated e-contracts, and complete escrow-based payments through their wallet. Admins can manage users, verifications, escrow/financial monitoring, and system categories & fees.

2) Iteration 2 (Weeks 8 – 9)

Intelligent Matching, Recruitment & Engagement Management

| FT-ID | Feature name | Priority | Module | UC-ID | SCR-ID |
| --- | --- | --- | --- | --- | --- |
| FT-16 | AI Recommendation | Should | Matchmaking | UC-62, UC-63, UC-64 | SCR-13 |
| FT-17 | Dynamic Weight Matching | Must | Matchmaking | UC-62 | SCR-14, SCR-52 |
| FT-20 | Availability & Calendar Sync | Should | Profile & Verification | UC-12, UC-13 | SCR-29 |
| FT-22 | Schedule Conflict Detection | Must | Class Life-cycle | UC-18, UC-25 | SCR-52 |
| FT-49 | Center Tutor Roster Management | Should | Class Life-cycle | UC-24 | SCR-25 |
| FT-32 | Class Disruption & Replacement | Must | Class Life-cycle | UC-26, UC-28, UC-29, UC-30 | SCR-65 |
| FT-27 | Refund Processing | Must | Smart Escrow Wallet | UC-42, UC-50, UC-51 | SCR-43 |
| FT-28 | Dispute Submission & Handling | Must | Dispute & Resolution | UC-48, UC-49 | SCR-44 |
| FT-38 | Complaint Management | Must | Dispute & Resolution | UC-49, UC-52 | SCR-38, SCR-56 |
| FT-29 | Submit & Manage Review | Must | Review & Reputation | UC-53, UC-54, UC-55 | SCR-47, SCR-48 |
| FT-30 | Reputation Score Calculation | Must | Review & Reputation | UC-53 | SCR-49 |
| FT-33 | Recruitment Campaign Management | Must | Tutor Recruitment | UC-68, UC-70 | SCR-23 |
| FT-34 | Recruitment Application & Pipeline | Must | Tutor Recruitment | UC-69, UC-71 | SCR-24, SCR-26 |
| FT-40 | Dashboard Analytics | Must | Operations Dashboard | UC-56, UC-47 | SCR-53, SCR-59 |

ℹ End-of-Iteration-2 outcome: [Describe what end-to-end scenario is now possible — e.g. 'BF-01 and BF-02 functional end-to-end, excluding the interview step.']

The platform now offers AI-powered tutor/class/job recommendations with dynamic-weight matching, calendar sync and schedule-conflict detection. Classes can be disrupted, replaced or terminated with refunds; disputes and complaints are raised and resolved; reviews feed a reputation score. Centers can post recruitment and evaluate applicants, while admins gain operational dashboard analytics.

3) Iteration 3 (Weeks 10 – 11)

Platform Governance, User Engagement, and Production Readiness

| FT-ID | Feature name | Priority | Module | UC-ID | SCR-ID |
| --- | --- | --- | --- | --- | --- |
| FT-03 | Password Recovery | Must | Auth & RBAC | UC-03, UC-04 | SCR-04, SCR-05 |
| FT-35 | Parent-Child Account Linking | Must | Auth & RBAC | UC-05, UC-06 | SCR-27 |
| FT-11 | Favorite Tutor | Could | Advanced Search | UC-27 | SCR-12 |
| FT-19 | Real-Time Notification | Must | Messaging & Notification | UC-35, UC-37 | SCR-36, SCR-37 |
| FT-45 | Notification Center | Should | Messaging & Notification | UC-37 | SCR-36 |
| FT-51 | AI Chatbot Support | Should | Smart Chatbot Advisor | UC-65 | SCR-50 |
| FT-23 | FAQ & Support Request Management | Should | Smart Chatbot Advisor | UC-66, UC-67 | SCR-38, SCR-63 |
| FT-46 | Activity Timeline | Should | Class Life-cycle | UC-21, UC-23 | SCR-21 |
| FT-42 | Report User or Class | Should | Dispute & Resolution | UC-52 | SCR-56 |
| FT-43 | Enforce Penalties / Block User | Must | Operations Dashboard | UC-60 | SCR-54, SCR-32 |
| FT-44 | Circumvention & Anomaly Detection | Must | Operations Dashboard | UC-59, UC-60 | SCR-32, SCR-33, SCR-57 |
| FT-41 | Audit Log | Should | Operations Dashboard | UC-61 | SCR-61 |

ℹ End-of-Iteration-3 outcome: [Fully complete system — all Business Flows, all FT-IDs, all background jobs live.]

Full account self-service (password recovery, parent–child linking) and engagement features (favorites, real-time notifications, notification center, AI chatbot & FAQ) are live. Governance is complete: admins detect platform circumvention, enforce penalties/block users, moderate reports, and trace activity via audit logs and class activity timelines — bringing the platform to production readiness.

# 4. Risks and Mitigations

| # | Risk | Prob | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| R01 | Reliance on third-party services and APIs may affect development and integration schedules. | Medium | Medium | Test with WireMock stubs; fall back to manual entry if integration fails. |
| R02 | Changes in requirements after approval may lead to scope creep and project delays. | Medium | High | Enforce strict ChangeLog controls; defer low-priority features with PO if needed. |
| R03 | AI-based matching and real-time communication features may require more effort than initially estimated. | Medium | High | Apply strict prompt engineering and validation; fall back to static rule-based results. |
| R04 | Unavailability of key team members may impact project continuity and delivery schedule. | Medium | Medium | Cross-train members via shared knowledge base; reassign tasks or escalate to instructor. |
| R05 | Ineffective communication and task coordination may delay project milestones. | Low | High | Track tasks via centralized Kanban; PM reallocates delayed tasks immediately. |

# 5. Communication Plan

| Meeting | Frequency | Duration | Participants |
| --- | --- | --- | --- |
| Daily team meeting | Every working day | 15 min | All members |
| Weekly meeting | Every Sunday | 15 min | All members |
| Supervisor meeting | Every Wednesday/Saturday | 1 hour | All members + Supervisor |
| Mentor meeting | Every Tuesday & Friday | 30 min | All members + Mentor |
| Task assignment and tracking | Continuous (Daily) | 5 min | PM + Assigned members |
| Source code management | Continuous | 30 min | All members |
| UI/UX discussion | During UI/UX phases | 2 hour | All members |
| Testing & Bug reporting | During testing phases | 30 min | Tester Tea |
| Documentation review | Before submission deadlines | 1 hour | All members |
| Final defense preparation meeting | During final 2 weeks | 30 min | All members |

# 6. Configuration Management

## 6.1 Document Management

[Describe how you would manage project documents: the platform, document folder structures, and their changes/versions]

1) Document Storage and Organization

All major project artifacts—including Reports 1–7, the Software Requirements Specification (SRS), Software Design Description (SDD), test documents, user guides, and meeting minutes—are centrally stored and managed within categorized folders on Google Drive. This cloud-based infrastructure ensures seamless collaboration, prevents data fragmentation, and provides an organized repository for all academic and technical files. The Project Manager is responsible for organizing these folders, reviewing contents, and ensuring that all artifacts are correctly aligned with the university's graduation milestones.

2) Naming Convention and Version Control

To maintain structural clarity and track document updates, the team enforces a strict, standardized naming convention that embeds the document title, version number, and last modification date (e.g., TCS_[Document_Name] v[X.X]). Minor edits during internal collaboration increment the decimal version (e.g., v1.1), while major milestones or final advisor-approved versions advance the principal number (e.g., v2.0). Google Docs' built-in revision history is heavily utilized to log exact changes, maintain backup copies of critical drafts, and allow the team to roll back to previous iterations if necessary.

3) Access Control and Change Review

Access control is managed through Google Drive's permission settings, granting full editing rights exclusively to internal team members while providing read-only access to external stakeholders, such as the thesis advisor, when feedback is required. Before any critical document is finalized for a milestone submission, a mandatory peer review process is initiated within the team to ensure quality, accurate formatting, and total consistency across all chapters. This collaborative validation ensures that no unauthorized or unverified changes slip into the final reports presented to the graduation committee.

## 6.2 Source Code Management

[Describe how you would manage project source codes & their changes/versions]

1) Branching Strategy

| Branching | Purpose | Naming Convention | Protection |
| --- | --- | --- | --- |
| main | Production code | main | Required reviews, CI passing |
| develop | Integration branch | develop | Required reviews |
| feature/ | New features | feature/Login | CI optional |
| bugfix/ | Bug fixes | bugfix/issue-XX-otp | CI optional |
| hotfix/ | Production fixes | hotfix/description | Fast-track review |
| release/ | Release preparation | release/v1.0.0 | Release manager |

2) Commit Conventions

| Type | Description | Example |
| --- | --- | --- |
| feat | New feature | feat: add user login |
| fix | Bug fix | fix: resolve class conflict |
| docs | Documentation | docs: update API documentation |
| style | Formatting | style: format code with prettier |
| refactor | Code improvement | refactor: extract auth service |
| test | Adding tests | test: add unit tests for class |
| chore | Maintenance | chore: update dependencies |
| pref | Performance | pref: optimize query for search |
| ci | CI/CD | ci: add GitHub Actions workflow |

3) Code Review and Integration Process

| Steps | Description |
| --- | --- |
| Create branch | $ git checkout -b feature/User Login |
| Make change & commit | $ git add . $ git commit -m “feat: add login form” |
| Push to remote | $ git push origin feature/User Login |
| Create pull request | 1. GitHub PR Template 2. Select reviewers 3. Link to issue |
| CI/CD pipeline | 1. Lint check 2. Unit tests 3. Build check 4. Security scan |
| Code review | 1. At least 2 approvals required 2. All comments resolved 3. All checks passing |
| Merge | 1. Squash and marge 2. Delete branch 3. Auto-deploy to staging |

## 6.3 Tools & Infrastructures

[List out all the tools or infrastructurs and versions (if any) that you would use for yourproject]

| Category | Tools / Infrastructure |
| --- | --- |
| Technology | ReactJS (Front-End), Spring Boot (Back-End), RESTful API, WebSocket |
| Database | MySQL 8.0 CE, Firebase |
| IDEs/Editors | IntelliJ IDEA 2025.1, WebStorm 2025.1.3 |
| Diagramming | Visual Paradigm, PlantUML, draw.io v28.1.2 |
| Documentation | MS Office 2019, Google Docs / Sheets / Slides |
| Version Control | GitHub (Source Codes), Google Drive (Documents) |
| Deployment server | Amazon Web Service |
| Project management | Jira: tasks, features; Google sheet: tasks, time logs, defects, issues. |